## Weekly Tracker
Target Index | Week # | Month | Phase | Focus Area | Weekday Tasks (1-2 hrs/day) | Weekend Target / Milestone (4-6 hrs) | Status | Notes / Blockers
1 | Week 1 | Month 1 | Phase 1: Engineering Foundations | Language setup & syntax basics | Install IDE/JDK or Python; daily syntax drills (variables, loops, conditionals) | Write 10 small syntax practice programs; set up GitHub repo for practice code | In Progress
2 | Week 2 | Month 1 | Phase 1: Engineering Foundations | Control flow & collections | Practice arrays/lists, maps/dictionaries, sets; daily 30-min coding drill | Build a program that processes a list of test data records (dedupe, sort, filter) | Not Started
3 | Week 3 | Month 1 | Phase 1: Engineering Foundations | OOP fundamentals I | Classes, objects, encapsulation; daily small class-design exercises | Model a 'TestCase' and 'TestSuite' class with attributes and methods | Not Started
4 | Week 4 | Month 1 | Phase 1: Engineering Foundations | OOP fundamentals II | Inheritance, polymorphism, interfaces | Extend Week 3 model with subclasses (UITestCase, APITestCase) using inheritance | Not Started
5 | Week 5 | Month 2 | Phase 1: Engineering Foundations | Exception handling & file I/O | Custom exceptions, try/catch patterns; reading CSV/JSON files | Build a script that reads test data from CSV and handles malformed rows gracefully | Not Started
6 | Week 6 | Month 2 | Phase 1: Engineering Foundations | HTTP & API fundamentals | HTTP verbs/status codes/headers; call a REST API from code (not Postman) | Write a script that calls a public API (reqres.in) and prints structured results | Not Started
7 | Week 7 | Month 2 | Phase 1: Engineering Foundations | SQL fundamentals | SELECT, JOIN, GROUP BY, subqueries on a sandbox DB | Write 10 validation queries against a sample e-commerce schema | Not Started
8 | Week 8 | Month 2 | Phase 1: Engineering Foundations | SQL advanced + MongoDB basics | Window functions; MongoDB find/aggregate basics | Write 3 complex validation queries + 3 MongoDB queries on sample data | Not Started
9 | Week 9 | Month 3 | Phase 1: Engineering Foundations | Clean code & design patterns I | Naming, single-responsibility functions; Factory & Singleton patterns | Refactor Week 5-6 scripts using clean code principles | Not Started
10 | Week 10 | Month 3 | Phase 1: Engineering Foundations | Page Object Model + Git | POM concept; Git branching, pull requests, resolving conflicts | Create a GitHub repo with proper branching workflow for practice code | Not Started
11 | Week 11 | Month 3 | Phase 1: Engineering Foundations | Milestone project build | Build: CSV -> API call -> validate -> log results console app | Complete first full working version of the milestone project | Not Started
12 | Week 12 | Month 3 | Phase 1: Engineering Foundations | Milestone project polish | Review, refactor, add exception handling + README documentation | TARGET: Phase 1 milestone project pushed to GitHub with clear README | Not Started
13 | Week 13 | Month 4 | Phase 2: Automation Engineering | Playwright basics | Install Playwright; write first scripts using locators and actions | Automate login + navigation flow on a demo site (saucedemo.com) | Not Started
14 | Week 14 | Month 4 | Phase 2: Automation Engineering | Playwright advanced | Auto-waiting, assertions, fixtures, test hooks | Automate a full checkout flow with assertions at each step | Not Started
15 | Week 15 | Month 4 | Phase 2: Automation Engineering | Framework architecture design | Plan layered design: Test / Page / Utility / Config layers | Draft framework architecture diagram + folder structure on paper/doc | Not Started
16 | Week 16 | Month 4 | Phase 2: Automation Engineering | Page Object Model implementation | Implement POM layer for demo site flows | Refactor Week 13-14 scripts into a proper POM structure | Not Started
17 | Week 17 | Month 5 | Phase 2: Automation Engineering | Test data management | Fixtures, data builders, avoiding hardcoded data | Add a data builder/fixture layer to your framework | Not Started
18 | Week 18 | Month 5 | Phase 2: Automation Engineering | Reporting integration | Integrate Allure or Extent Reports | Generate a full HTML test report from a framework run | Not Started
19 | Week 19 | Month 5 | Phase 2: Automation Engineering | Parallel & cross-browser execution | Configure parallel test execution; run on Chromium + Firefox | Confirm suite runs in parallel across 2 browsers successfully | Not Started
20 | Week 20 | Month 5 | Phase 2: Automation Engineering | Flaky test diagnosis | Study race conditions, improper waits, test isolation issues | Intentionally break a test, diagnose root cause, document the fix | Not Started
21 | Week 21 | Month 6 | Phase 2: Automation Engineering | API automation basics | Rest Assured / Playwright API / Python requests + pytest setup | Automate 5 CRUD API test cases for a public API | Not Started
22 | Week 22 | Month 6 | Phase 2: Automation Engineering | Auth testing & schema validation | API key/OAuth2/session auth testing; JSON Schema validation | Add auth test cases + schema validation checks to API suite | Not Started
23 | Week 23 | Month 6 | Phase 2: Automation Engineering | Contract testing + CI setup | Pact concept overview; set up GitHub Actions workflow YAML | Get a basic GitHub Actions pipeline running your API suite on push | Not Started
24 | Week 24 | Month 6 | Phase 2: Automation Engineering | Full framework + CI integration | Merge UI + API suites into CI pipeline with reporting | TARGET: Project 1 (UI+API framework with CI) complete on GitHub | Not Started
25 | Week 25 | Month 7 | Phase 3: Performance, Security, DB Depth | Performance testing concepts | Load, stress, spike, soak, scalability testing definitions | Write a 1-page comparison of when to use each performance test type | Not Started
26 | Week 26 | Month 7 | Phase 3: Performance, Security, DB Depth | k6 basics | Install k6; write first load test script against your API | Run a basic load test against your Project 2 API and capture results | Not Started
27 | Week 27 | Month 7 | Phase 3: Performance, Security, DB Depth | k6 advanced | Thresholds, stages, ramping load patterns | Build a spike test scenario and a soak test scenario in k6 | Not Started
28 | Week 28 | Month 7 | Phase 3: Performance, Security, DB Depth | Performance analysis & reporting | Analyze p50/p95/p99 latency, throughput, error rate | TARGET: Complete Project 4 performance report with graphs and analysis | Not Started
29 | Week 29 | Month 8 | Phase 3: Performance, Security, DB Depth | OWASP Top 10 (part 1) | Injection, broken authentication concepts + basic test approach | Write test cases for 2 OWASP categories against your API | Not Started
30 | Week 30 | Month 8 | Phase 3: Performance, Security, DB Depth | OWASP Top 10 (part 2) | Broken access control, security misconfiguration | Write test cases for 2 more OWASP categories | Not Started
31 | Week 31 | Month 8 | Phase 3: Performance, Security, DB Depth | Authorization/IDOR testing | Hands-on IDOR testing against your API suite | Add 3-5 IDOR/authorization test cases to Project 2 | Not Started
32 | Week 32 | Month 8 | Phase 3: Performance, Security, DB Depth | Session & API security testing | Session fixation, token expiry, rate limiting, data exposure checks | Add session + rate-limit test cases to your API suite | Not Started
33 | Week 33 | Month 9 | Phase 3: Performance, Security, DB Depth | Security tooling basics | Burp Suite Community / OWASP ZAP: intercept & modify requests | Intercept and modify 3 requests manually to test validation handling | Not Started
34 | Week 34 | Month 9 | Phase 3: Performance, Security, DB Depth | Advanced SQL for data integrity | Multi-table joins, orphaned records, duplicate detection queries | Write 5 data integrity validation queries against sample schema | Not Started
35 | Week 35 | Month 9 | Phase 3: Performance, Security, DB Depth | MongoDB aggregation & schema-less validation | Aggregation pipeline stages; schema-less data validation challenges | Write 3 MongoDB aggregation queries for data validation scenarios | Not Started
36 | Week 36 | Month 9 | Phase 3: Performance, Security, DB Depth | Phase 3 consolidation | Merge security + DB validation tests into Project 2 | TARGET: Security, performance, and DB tests merged into portfolio projects | Not Started
37 | Week 37 | Month 10 | Phase 4: AI-Native QA + Portfolio | Prompt engineering for QA | Learn structured prompting: context, constraints, explicit ask | Write 5 prompts to generate edge-case test scenarios from a sample requirement | Not Started
38 | Week 38 | Month 10 | Phase 4: AI-Native QA + Portfolio | AI-assisted test generation | Use Claude/Copilot to draft test scripts; practice reviewing/correcting output | Draft 5 test cases with AI, then document your review/correction process | Not Started
39 | Week 39 | Month 10 | Phase 4: AI-Native QA + Portfolio | AI-assisted maintenance & debugging | Use AI to fix broken locators/assertions and debug stack traces | Break a test on purpose, use AI to help diagnose and fix it, verify manually | Not Started
40 | Week 40 | Month 10 | Phase 4: AI-Native QA + Portfolio | AI testing tools landscape | Research self-healing tools, AI code review assistants | Write a short comparison doc of 3 AI testing tools and their real capabilities | Not Started
41 | Week 41 | Month 11 | Phase 4: AI-Native QA + Portfolio | Testing AI/ML applications | Non-determinism in AI output; evaluation basics (golden datasets, rubrics) | Design an evaluation rubric for a hypothetical AI feature | Not Started
42 | Week 42 | Month 11 | Phase 4: AI-Native QA + Portfolio | AI/LLM test project - start | Build or use a simple prompt-based feature; start test plan | Start Project 5: draft test strategy for non-deterministic output | Not Started
43 | Week 43 | Month 11 | Phase 4: AI-Native QA + Portfolio | Prompt testing & output validation | Implement prompt variation tests; validate output format/accuracy | Implement 5-8 automated checks for AI output validation | Not Started
44 | Week 44 | Month 11 | Phase 4: AI-Native QA + Portfolio | Responsible AI testing | Bias/safety checks; refusal behavior testing where expected | TARGET: Complete Project 5 (AI/LLM testing project) with documentation | Not Started
45 | Week 45 | Month 12 | Phase 4: AI-Native QA + Portfolio | Mobile automation basics | Appium setup; simple Android/iOS test concepts | Automate one simple flow on a demo mobile app with Appium | Not Started
46 | Week 46 | Month 12 | Phase 4: AI-Native QA + Portfolio | Portfolio polish | Documentation pass across all projects; clean up READMEs | All 5 portfolio projects have clear, professional documentation | Not Started
47 | Week 47 | Month 12 | Phase 4: AI-Native QA + Portfolio | Resume & profile update | Update resume/LinkedIn to reflect new skill stack and projects | Resume and LinkedIn updated with quantifiable project outcomes | Not Started
48 | Week 48 | Month 12 | Phase 4: AI-Native QA + Portfolio | Mock interviews I | Practice technical & automation framework questions | Complete 2 mock interview sessions on technical/automation topics | Not Started
49 | Week 49 | Month 12 | Phase 4: AI-Native QA + Portfolio | Mock interviews II | Practice scenario-based, SQL, and CI/CD questions | Complete 2 mock interview sessions on scenario/SQL/CI-CD topics | Not Started
50 | Week 50 | Month 12 | Phase 4: AI-Native QA + Portfolio | Mock interviews III | Practice leadership/communication questions; rehearse project walkthroughs | Deliver a confident 5-minute walkthrough of each portfolio project | Not Started
51 | Week 51 | Month 12 | Phase 4: AI-Native QA + Portfolio | Job search / internal transition prep | Apply to mid-level roles or prepare internal promotion conversation | Submit applications or schedule a promotion discussion with your manager | Not Started
52 | Week 52 | Month 12 | Phase 4: AI-Native QA + Portfolio | Full retrospective | Review learning log; identify remaining gaps; plan next 90 days | TARGET: Ready for Mid-Level SQA interviews with full portfolio and plan for what's next | Not Started

## Dashboard
12-Month SQA Roadmap - Progress Dashboard
Metric | Value | Phase | Completion %
Total Weeks | 52 | Phase 1: Engineering Foundations | 0%
Completed | 0 | Phase 2: Automation Engineering | 0%
In Progress | 1 | Phase 3: Performance, Security, DB Depth | 0%
Not Started | 51 | Phase 4: AI-Native QA + Portfolio | 0%
Blocked | 0
Overall Completion % | 0%
Legend: Update the 'Status' column in the Weekly Tracker sheet each week.
This dashboard recalculates automatically from that column.